## Yifei
Task # | Title | Description | Start Date | Deadline | Completed | Remaining | Status
Formulas:
Completed = IF([Start Date]<>"",IF(TODAY()>=[Start Date],TODAY()-[Start Date],"NA"),"")
Remaining = IF([Start Date]<>"",IF([Deadline]<>"",IF(TODAY()>=[Start Date], [Deadline]-TODAY(),[Deadline]-[Start Date]),""),"")

## Jimmy
Task # | Title | Description | Start Date | Deadline | Completed | Remaining | Status
Formulas:
Completed = IF([Start Date]<>"",IF(TODAY()>=[Start Date],TODAY()-[Start Date],"NA"),"")
Remaining = IF([Start Date]<>"",IF([Deadline]<>"",IF(TODAY()>=[Start Date], [Deadline]-TODAY(),[Deadline]-[Start Date]),""),"")

## Jake
Task # | Title | Description | Start Date | Deadline | Completed | Remaining | Status
Formulas:
Completed = IF([Start Date]<>"",IF(TODAY()>=[Start Date],TODAY()-[Start Date],"NA"),"")
Remaining = IF([Start Date]<>"",IF([Deadline]<>"",IF(TODAY()>=[Start Date], [Deadline]-TODAY(),[Deadline]-[Start Date]),""),"")

## Jawad
Task # | Title | Description | Start Date | Deadline | Completed | Remaining | Status
1 | SDD -Primitives | Terminate() | 2011-10-07 | 2011-10-11 | 6 | -2 | Complete
2 | SDD -Primitives | Send Console Chars() | 2011-10-08 | 2011-10-12 | 5 | -1 | Complete
3 | SDD -Primitives | Get Console Chars() | 2011-10-09 | 2011-10-13 | 4 | 0 | Complete
4 | SDD -Primitives | Request delay() | 2011-10-10 | 2011-10-14 | 3 | 1 | Complete
5 | SDD -Primitives | Change Priority() | 2011-10-11 | 2011-10-15 | 2 | 2 | Complete
6 | SDD -Primitives | Get Trace Buffers () | 2011-10-12 | 2011-10-16 | 1 | 3 | Complete
Formulas:
Completed = IF([Start Date]<>"",IF(TODAY()>=[Start Date],TODAY()-[Start Date],"NA"),"")
Remaining = IF([Start Date]<>"",IF([Deadline]<>"",IF(TODAY()>=[Start Date], [Deadline]-TODAY(),[Deadline]-[Start Date]),""),"")

## Timeline Data
MTE 241 Project Timeline
Task # | Title | Description | Start Date | Deadline | Completed | Remaining | Status | Notes | NOTES: | Completed' and 'Remaining' fields contain the number of days completed or left
1 | SDD (Primitives) | User API and kernal primitives | 2011-10-07 | 2011-10-11 | 6 | -2 | Pending | Yifei needs to complete primitives
2
Formulas:
Completed = IF([Start Date]<>"",IF(TODAY()>=[Start Date],TODAY()-[Start Date],"NA"),"")
Remaining = IF([Start Date]<>"",IF([Deadline]<>"",IF(TODAY()>=[Start Date], [Deadline]-TODAY(),[Deadline]-[Start Date]),""),"")